LPM Communications Plan		Last updated:  15/11/16

| Who | What | How | Who | When | Why | Next |
| --- | --- | --- | --- | --- | --- | --- |
| Core team | Central location for all project info | Edge page on LPI site | AM | Update weekly |  | 18/11 |
|  | Regular project catch up | Face to face | AM | Fortnightly | Update. Hold a/c to tasks. Planning. Trouble-shooting. Ideas sharing… | 22/11 |
| Whole project team | Project update | Standard report with cover email | AM | Fortnightly | General update. Keep informed. Oppo to ask Qs. Ask for ideas, Qs, involvement, doc sharing | 25/11 |
| Interested parties | Project update | Email – extracts from reports etc. | AM | Monthly | General update. Oppo to ask Qs | 25/11 |
| 'Input from' people | Project update | Email – extracts from reports etc. | AM | Monthly | General update. | 25/11 |
|  | Requests for input | Email, phone | AM | Ad hoc | Expertise needed in project |  |
| Sponsors & Project Board | Project update | Email – extracts from reports etc. | AM | Monthly | Keep connected to project – no surprises. Series of yeses. | 25/11 |
|  | Help requests | Email, phone | AM | Ad hoc | Influence needed in project |  |
|  | Milestone reviews | Face to face | AM | Stage ends | Check objectives & direction still relevant |  |
| Experimenters | Project update | Email – extracts from reports etc. | AM | Monthly | Keep connected to project & informed. Oppo to ask Qs. | 25/11 |
| Partaking depts. / partners | Communicate successes & rollout plans | Email | AM | Later stages | To advise of successes, encourage involvement, gain momentum |  |